## Phase map
FOLIO / PHASE MAP
Month 0 assumes October 2026. Gates override dates. Phases 1–2 remain native macOS; at least 20% capacity is reserved for hardening.
Phase | Outcome | Indicative dates | Relative months | Platforms | Scope | Exit gate | FolioDev
1 | Native foundation | Q4 2026–Q3 2027 | M0–11 | macOS only | Local Markdown; editor; graph; Timeline / Kanban; reviewed .rdm; optional on-device capture | No acknowledged-save loss; accessibility; reviewed encryption; install / upgrade and performance gates | Disabled in production
2 | Native depth + trusted collaboration | Q4 2027–Q3 2028 | M12–23 | macOS only | 100k-note optimisation; multi-window; portable core; E2EE alpha / gated beta | Native quality preserved; differential core tests; external protocol review; recovery and revocation tests | Disabled in production; internal R&D only
3 | Windows parity, then build workflow | Q4 2028–Q3 2029 | M24–35 | Windows + macOS | Tauri / Rust gate; Notes parity; dual-platform QA; later opt-in source / LSP pane | Windows accessibility / IME and format parity; signed update recovery; Dev permission review | Optional preview only after Windows Notes parity
4 | Android vault companion | Q4 2029–Q3 2030 | M36–47 | Android preview | Read-only first; encrypted cache; offline browse / search; later limited edits | Process-death recovery; safe background sync; key-loss rehearsal; no unsupported schema writes | Not included on Android

## Backlog
FOLIO / BACKLOG
Priorities: P0 safety/core; P1 high-value depth; P2 optional. Month offsets are indicative envelopes, not effort. Dependencies are required handoffs and may overlap; sprint planning must specify finish-to-start gates. All work is proposed.
ID | Phase | Priority | Work package | Start month | End month | Dependencies | Owner discipline | Exit evidence | Status
B01 | 1 | P0 | Threat model + architecture ADRs | 0 | 1 | — | Technical lead / security | Boundaries, threat model, OS assumptions and trust prompts reviewed | Proposed
B02 | 1 | P0 | Representative fixtures + performance harness | 0 | 1 | — | Quality / performance | 1k / 10k / 100k fixtures; repeatable hardware measurements | Proposed
B03 | 1 | P0 | Native editor / IME vertical slice | 0 | 2 | B01,B02 | Native editor | Round-trip text, composition, undo and viewport budget proven | Proposed
B04 | 1 | P0 | Journal, atomic save + recovery | 0 | 3 | B01,B02 | Storage | Every acknowledged revision survives injected failure cases | Proposed
B05 | 1 | P0 | Launcher, file explorer + navigation | 2 | 4 | B03,B04 | Native UI | Notes active left; Dev disabled right; keyboard / focus flows | Proposed
B06 | 1 | P0 | Markdown, identity, links + import | 2 | 4 | B03,B04 | Documents | External edits, rename, ambiguous links and clone handling tested | Proposed
B07 | 1 | P0 | Local SQLite / FTS index | 3 | 5 | B06 | Search / storage | Rebuild-from-zero equivalence; bounded query latency | Proposed
B08 | 1 | P0 | Shared roadmap model, Kanban + Timeline | 5 | 7 | B06,B07 | Domain / UI | Status, dates and note links agree across projections | Proposed
B09 | 1 | P0 | Focused Metal graph + list equivalent | 5 | 7 | B07,B08 | Graphics | Visible node / edge budgets; idle drawing stops; keyboard equivalent | Proposed
B10 | 1 | P0 | .rdm encrypted store + checkpoints | 4 | 8 | B01,B04,B06 | Storage / security | Crypto vectors, parser fuzzing, restore and external review | Proposed
B11 | 1 | P1 | On-device capture / speech adapters | 6 | 9 | B03,B06 | AI / native | Availability / locale checks; deterministic fallback; review before apply | Proposed
B12 | 1 | P0 | Native installer + update fixtures | 7 | 9 | B05 | Release | Signed notarized stapled PKG; clean-machine upgrade / offline tests | Proposed
B13 | 1 | P0 | Accessibility + energy hardening | 7 | 10 | B05,B08,B09 | Quality / design | VoiceOver, IME, contrast, reduced motion and battery regression suite | Proposed
B14 | 1 | P0 | Beta evidence + FolioNotes 1.0 gate | 10 | 11 | B07,B08,B09,B10,B12,B13 | Release owner | 30-day quality window; no data-loss / critical-high security defects | Proposed
B15 | 2 | P0 | 100k-note and long-document optimisation | 12 | 15 | B14 | Performance | Stress budgets met with degradation, not unbounded memory | Proposed
B16 | 2 | P1 | Native multi-window refinement | 12 | 16 | B14 | Native UI | Per-window focus / selection / undo and workspace lifetime tested | Proposed
B17 | 2 | P1 | Gantt / dependency planning depth | 14 | 18 | B08,B14 | Roadmaps | Cycles, dates and unscheduled entities handled consistently | Proposed
B18 | 2 | P0 | Format freeze + cross-language fixtures | 14 | 16 | B10,B14 | Domain / security | .rdm v1 logical conformance corpus and schema policy fixed | Proposed
B19 | 2 | P0 | Incremental Rust core extraction | 15 | 18 | B18 | Core | Differential tests pass; native adapters retain ownership of UI | Proposed
B20 | 2 | P0 | CRDT convergence / compaction evaluation | 16 | 19 | B18 | Sync | Unicode, undo, long offline and history-growth benchmarks | Proposed
B21 | 2 | P0 | MLS / identity / membership integration | 16 | 20 | B01,B18 | Security | Role and epoch ordering; device verification; key deletion policy | Proposed
B22 | 2 | P1 | Invite-only E2EE alpha | 19 | 21 | B19,B20,B21 | Sync / native | Encrypted operation transport, rollback detection and recovery exercises | Proposed
B23 | 2 | P0 | External collaboration integration review | 20 | 22 | B22 | Independent security review | No unresolved critical/high findings; documented metadata exposure | Proposed
B24 | 2 | P0 | Gated collaboration beta approval | 22 | 23 | B15,B23 | Release owner | Revocation, partition and recovery evidence; GA separately approved | Proposed
B25 | 2 | P2 | Isolated FolioDev source-link R&D | 20 | 23 | B19 | Developer tools | Stable repo / symbol mapping; production launcher remains disabled | Proposed
B26 | 3 | P0 | Windows Tauri / Rust vertical slice | 24 | 26 | B19,B24 | Windows team | IME, screen reader, DPI, native dialogs and graph spike | Proposed
B27 | 3 | P0 | Windows shell go / no-go | 26 | 26 | B26 | Technical lead | Tauri meets gates or explicit native-shell pivot | Proposed
B28 | 3 | P0 | FolioNotes Windows workflow parity | 27 | 30 | B27 | Windows / core | Vault, .rdm, search, graph and planning acceptance matrix | Proposed
B29 | 3 | P0 | Cross-platform storage + sync conformance | 27 | 31 | B28 | Core / quality | Filesystem, format, keys and supported collab parity | Proposed
B30 | 3 | P0 | Windows release + upgrade hardening | 31 | 34 | B28,B29 | Release / quality | Signed artifacts; recovery and compatibility beta evidence | Proposed
B31 | 3 | P1 | Opt-in FolioDev preview on Mac + Windows | 34 | 35 | B25,B30 | Developer tools / security | Source links and code pane; reviewed LSP consent; no arbitrary execution | Proposed
B32 | 4 | P0 | Android read-only native shell | 36 | 39 | B19,B30 | Android team | Browse, read, search downloaded content and inspect plans | Proposed
B33 | 4 | P0 | Encrypted cache + offline import | 37 | 40 | B32 | Android / storage | Keystore wrapping and Storage Access Framework boundary tested | Proposed
B34 | 4 | P0 | Mobile device / background safety | 39 | 42 | B33 | Android / security | Revocation, process death and reconnect safety; schema preservation | Proposed
B35 | 4 | P1 | Limited light-edit alpha | 40 | 43 | B34 | Android / sync | Inbox capture, append and task toggle have durable outbox semantics | Proposed
B36 | 4 | P0 | Android preview hardening + scope review | 44 | 47 | B34,B35 | Release / quality | Low-memory, key-loss, migration and background tests; editing gated | Proposed

## Quarter view
FOLIO / QUARTER VIEW
Gantt shading is indicative. A phase cannot bypass its safety gate. Dependencies and acceptance evidence are on the Backlog sheet.
ID | Work package | Phase | Q4 2026 | Q1 2027 | Q2 2027 | Q3 2027 | Q4 2027 | Q1 2028 | Q2 2028 | Q3 2028 | Q4 2028 | Q1 2029 | Q2 2029 | Q3 2029 | Q4 2029 | Q1 2030 | Q2 2030 | Q3 2030
B01 | Threat model + architecture ADRs | 1 | ●
B02 | Representative fixtures + performance harness | 1 | ●
B03 | Native editor / IME vertical slice | 1 | ●
B04 | Journal, atomic save + recovery | 1 | ● | ●
B05 | Launcher, file explorer + navigation | 1 | ● | ●
B06 | Markdown, identity, links + import | 1 | ● | ●
B07 | Local SQLite / FTS index | 1 |  | ●
B08 | Shared roadmap model, Kanban + Timeline | 1 |  | ● | ●
B09 | Focused Metal graph + list equivalent | 1 |  | ● | ●
B10 | .rdm encrypted store + checkpoints | 1 |  | ● | ●
B11 | On-device capture / speech adapters | 1 |  |  | ● | ●
B12 | Native installer + update fixtures | 1 |  |  | ● | ●
B13 | Accessibility + energy hardening | 1 |  |  | ● | ●
B14 | Beta evidence + FolioNotes 1.0 gate | 1 |  |  |  | ●
B15 | 100k-note and long-document optimisation | 2 |  |  |  |  | ● | ●
B16 | Native multi-window refinement | 2 |  |  |  |  | ● | ●
B17 | Gantt / dependency planning depth | 2 |  |  |  |  | ● | ● | ●
B18 | Format freeze + cross-language fixtures | 2 |  |  |  |  | ● | ●
B19 | Incremental Rust core extraction | 2 | [5 empty] | ● | ●
B20 | CRDT convergence / compaction evaluation | 2 | [5 empty] | ● | ●
B21 | MLS / identity / membership integration | 2 | [5 empty] | ● | ●
B22 | Invite-only E2EE alpha | 2 | [6 empty] | ● | ●
B23 | External collaboration integration review | 2 | [6 empty] | ● | ●
B24 | Gated collaboration beta approval | 2 | [7 empty] | ●
B25 | Isolated FolioDev source-link R&D | 2 | [6 empty] | ● | ●
B26 | Windows Tauri / Rust vertical slice | 3 | [8 empty] | ●
B27 | Windows shell go / no-go | 3 | [8 empty] | ●
B28 | FolioNotes Windows workflow parity | 3 | [9 empty] | ● | ●
B29 | Cross-platform storage + sync conformance | 3 | [9 empty] | ● | ●
B30 | Windows release + upgrade hardening | 3 | [10 empty] | ● | ●
B31 | Opt-in FolioDev preview on Mac + Windows | 3 | [11 empty] | ●
B32 | Android read-only native shell | 4 | [12 empty] | ● | ●
B33 | Encrypted cache + offline import | 4 | [12 empty] | ● | ●
B34 | Mobile device / background safety | 4 | [13 empty] | ● | ●
B35 | Limited light-edit alpha | 4 | [13 empty] | ● | ●
B36 | Android preview hardening + scope review | 4 | [14 empty] | ● | ●

## Release gates
FOLIO / RELEASE GATES
A failed gate blocks the relevant feature or release. Dates and visual polish do not override safety evidence.
ID | Phase | Gate | Required outcome | Owner | Evidence
G1 | Phase 1 | Durability | No loss of acknowledged revisions under supported fault model | Storage + quality | Crash at write barriers, disk-full, permission loss, external edit, restore
G2 | Phase 1 | Native quality | Keyboard, VoiceOver, IME, contrast and reduced motion pass | Native lead + design | Recorded task walkthroughs and regression suites
G3 | Phase 1 | Encrypted .rdm | Independent review; tampering rejected; no plaintext residue | Security owner | Vectors, parser fuzzing, key recovery and migration tests
G4 | Phase 1 | Release safety | Notarized / stapled artifact installs and updates correctly | Release owner | Clean machines, offline checks, stable identifiers and relocation policy
G5 | Phase 2 | Shared core | Differential logical output and recovery semantics match | Core lead | Cross-language golden corpus; FFI overhead and native quality evidence
G6 | Phase 2 | Collaboration beta | External review; membership races and offline convergence pass | Security + sync | Malicious relay, replay, partitions, recovery and revoked-device exercises
G7 | Phase 3 | Windows parity | Core workflows, format and accessibility parity | Windows lead | IME / DPI / filesystem / encrypted key / update matrix
G8 | Phase 3 | Dev activation | Repo-scoped consent and untrusted-source containment | Dev tools + security | No executable imports; bounded LSP privileges; link-repair tests
G9 | Phase 4 | Read-only preview | No schema writes; encrypted cache and process-death recovery | Android lead | Offline search scope, export/import, storage provider and key-loss tests
G10 | Phase 4 | Light editing | Acknowledged outbox edits survive kill / reconnect | Android + sync | Conflict, revocation, low-memory, background restrictions and recovery

## Risks
FOLIO / RISKS
Qualitative planning risks, not measured incident probabilities. Re-evaluate at each phase gate.
ID | Risk | Impact | Early window | Owner | Early signal | Mitigation
R1 | Editor edge cases | High | M0–1 | Native lead | IME, large-line or selection regressions | Spike before custom rendering; narrow adapter and preserve native text behaviour
R2 | Archive write cost | High | M4–8 | Storage lead | Slow checkpoints / large temporary-space demand | Encrypted working store; atomic checkpoint and progress; measured archive limits
R3 | CRDT history growth | High | M16–19 | Sync lead | Growing reopen time and memory | Benchmark compaction and long-offline histories before library commitment
R4 | Overstated E2EE guarantees | High | M16–23 | Security owner | Unclear recovery or history-key claims | External integration review; publish exact endpoints and metadata limitations
R5 | Mac quality lost in port | High | M24–35 | Product lead | Mac regressions / depleted native staffing | Ring-fence native capacity; shared core does not own the Mac UI
R6 | AI unavailability / harmful rewrite | Medium | M6–9 | AI lead | Silent fallback or source overwrite | Availability checks; deterministic formatter; review / revision-check / undo
R7 | Graph overload | Medium | M5–7 | Design + graphics | Users cannot find a neighbour or understand an edge | Local focus, bounded projections and equally capable list alternative
R8 | Dual source of truth | High | M2–7 | Domain lead | Rebuild loses authored roadmap fields | Portable authored metadata; index deletion/rebuild parity tests
R9 | Unrecoverable encryption surprises | High | M4–8 | Security + design | Unverified recovery setup | Rehearsal, recovery-key verification and honest lost-key consequences

## Performance
FOLIO / PERFORMANCE
All values are engineering targets, NOT benchmark results. Record build, OS, dataset seed, power mode and thermal state; use at least 30 runs for release percentile comparisons.
Metric | Reference condition | Proposed target | Measurement / fallback
Cold launcher | M1 / 8 GB, SSD, 60 Hz | p95 ≤ 1.5 s | No indexing / model initialisation on the launch path
Warm standard workspace | 10k notes / indexed | p95 ≤ 500 ms | Restore visible note before background reconciliation
Keystroke → glyph | 200 KiB note | p95 ≤ 16.7 ms; p99 ≤ 33 ms | Measure presentation, not just string mutation
Warm search, standard | 10k notes | p95 ≤ 100 ms | Exclude debounce; return first page
Warm search, stress | 100k notes | p95 ≤ 250 ms | Report index incompleteness; cancellable query
Durable local ACK | Reference storage, after coalescing | p95 ≤ 500 ms | Only show saved after the durability barrier
Graph interaction | 2k visible nodes / 8k edges | p95 frame ≤ 16.7 ms | Budget both labels and edges; 30 Hz low-power fallback
Idle CPU / memory | Standard vault, AI off, 5 minutes | Mean CPU <1% of one core; p95 RSS ≤350 MiB | Include helpers; record background noise and thermal state
Stress memory | 100k notes, AI off | ≤750 MiB | Bounded projections; no full-note preload
Initial standard index | 10k notes / 100 MiB Markdown | ≤30 s target | Editor remains responsive; progress / pause
Battery regression | Fixed 60-minute reference workflow | ≤10% energy regression vs prior release | Same hardware / OS; no absolute battery-life promise